## Basket (hidden)
| Project Report | [12 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
| PROJECT TITLE |  | BasketPort |  | Start Date | 2024-06-28 |  | Project Health | At Risk | Good | Great |  |  |  | Medium
| PROJECT MANAGER |  | Hesham Raafat |  | Deadline | 2025-05-15 | Stage 1 | Month | Augest |  | Sprint No. | 7 out of 12 |  | In Progress | High
Allocation | [7 empty] | Week | 1 |  | Schduling | Behind |  | Under Review
Senoirity | Name | Position | Peformance Rating | Quality Rating | Workload Low/Normal/High | Note | [7 empty] | Complete
| Hany Mohamed | Ui/Ux | No task | No task | Low | Yes
| Ahmed Abdel Fattah | Tech-Lead | 4 | 0 | Normal
| Ahmed Adel | Tester | 3 | 0 | Normal
| Mohamed Salah | Backend developer | 4 | 0 | Normal
| Moataz Gamal | Backend developer | 3 | 0 | Normal
| Omar Adly | Frontend developer | 4 | 0 | High
| Anwar Abdelmaksoud | Frontend developer | 5 | 0 | Normal
| Ahmed Hesham | Frontend developer | 4 | 0 | High
| Mustafa Ibrahim | Mobile Developer | 4 | 0 | High
| PROJECT DETAILS | [8 empty] | DELIVERABLES | HOURS
| STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | Tags | % DONE | Story Point | ESTIMATED HOURS | ACTUAL HOURS
| Product Module | [8 empty] | 100% | 6 | 30 | 56
| Complete | High | 2025-03-23 | 2025-04-23 | 30 | Fork Attarah Project | Mohamed Salah | Copy data base and backend from Attarah to Kassarh | Backend | 100% | 1 | 5 | 25
| Complete | High | 2025-03-24 | 2025-04-23 | 29 | Dashboard Adjustments | Mohamed Salah | Adjust the dashboards to fit with kassarh | Backend | 100% | 2 | 10 | 3
| Complete | High | 2025-03-25 | 2025-04-23 | 28 | UI design adjustments | Ahmed Hesham | Adjust logo and colors | frontend | 100% | 1 | 5 | 18
| Complete | High | 2025-03-26 | 2025-04-23 | 27 | Fork Attarah Project | Omar Adly | Copy UI from Attarah to Kassarh | frontend | 100% | 2 | 10 | 10
| On Hold | Low | 2025-03-23 |  |  | Pricing Structure | Mohamed Salah | apply the vriation to change the price | Backend | 75% | 3
| Complete | Medium | 2025-04-23 | 2025-04-23 |  | On Boarding Proccess | Omar Adly | Filling the User profile is mandatory | frontend | 100% | 1
| Complete | High |  |  |  | Adjust the mobile app UI from Attarah to Kassarh | Mustafa Ibrahim | Change the UI design to match Web design | Mobile | 100% | 3
| Actions and Recommendations |  | Inquiries |  | Issues |  | Actions | 5
| #1 | Action torem | #1 | Inquiries | #1 | Issues | Inquiries | 2
| #2 | ACtion torem | #2 | Inquiries | #2 | Issues | Issues | 2
| #3 | ACtion torem | #3 |  | #3
| #4 | ACtion torem | #4 |  | #4
| #5 | ACtion torem | #5 |  | #5
| #6 |  | #6 |  | #6
| #7 |  | #7 |  | #7

## Geftar
| Project Report | [12 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
| PROJECT TITLE |  | Geftar |  | Start Date | 2024-05-16 |  | Project Health | At Risk | Good | Great |  |  |  | Medium
| PROJECT MANAGER |  | Hesham Raafat |  | Deadline | 2025-05-15 | Product Module | Month | July |  | Sprint No. | 14 |  | In Progress | High
Allocation | [7 empty] | Week | 1&2 |  | Schduling | Ahead |  | Under Review
Senoirity | Name | Position | Peformance Rating | Quality Rating | Workload Low/Normal/High | Note | [7 empty] | Complete
Jr | Mustafa Ahmed | Ui/Ux | 4 | 4 | Low
tech-Lead | Aboelhassan Omran | Backend-Dev/ tech lead | 4 | 0 | High
Jr | Fatma Magdy | Tester | 4 | 0 | Normal
Jr | Loai Tarek | Backend-Dev | 4 | 0 | Normal
Jr | Mostafa Mohamed | Backend-Dev | 3 | 0 | Normal
Jr | Toka Yasser | Frontend-Dev | 4 | 0 | High
Jr | Ahmed Samy | Frontend-Dev | 5 | 0 | Normal
Jr | Mohamed Hafez | Frontend-Dev | 4 | 0 | High
Mid | Mustafa Ibrahim | Mobile Developer | 4 | 0 | High
Jr | Adel Hussien | Mobile Developer |  |  | Normal
| PROJECT DETAILS | [8 empty] | DELIVERABLES | HOURS
| STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | Tags | % DONE | Story Point | ESTIMATED HOURS | ACTUAL HOURS
| Product Module | [8 empty] | 75% | 87 | 169 | 0
| Complete | High | 2025-07-06 | 2025-07-17 | 11 | User Account Management | Aboelhassan Omran | Enhance user profile | Backend | 75% | 1 | 2
| In Progress | Low | 2025-07-06 | 2025-07-17 | 11 | Support & Information | Loai Tarek | FAQ section implementation | Backend |  | 2 | 4
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Order Customization | Mostafa Mohamed | Customization interactions for "Create Order" workflow | Backend |  | 3 | 5
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | User Communication | Mostafa Mohamed | Enhance pagination in Notification page | Backend |  | 1 | 1
| In Progress | Low | 2025-07-06 | 2025-07-17 | 11 | Order Customization | Loai Tarek | Implement skip step in "Create Order" | Backend |  | 1 | 2
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Cart Experience | Aboelhassan Omran | Show modal on "Add to Cart" with "Continue Shopping" and "View Cart" buttons | Frontend |  | 1 | 2
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Product Discovery | Mostafa Mohamed | Dynamic filter functionality for Products page | Backend |  | 2 | 3
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Order Customization | Mustafa Ibrahim | Implement back button in "Create Order" | Mobile |  | 1 | 1
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | SEO & Discovery | Aboelhassan Omran | SEO optimization for Product page | Backend |  | 8 | 18
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Security | Aboelhassan Omran | CSRF protection implementation | Backend |  | 5 | 12
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | Guest Access | Mostafa Mohamed | Guest token handling | Backend |  | 8 | 14
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | Payment & Wallet | Mostafa Mohamed | Fix for failed wallet partial flow | Backend |  | 2 | 4
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | User Account Management | Mustafa Ibrahim | New profile UI | Mobile |  | 8 | 14
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Order Management | Adel Hussien | Orders separation | Mobile |  | 3 | 6
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Order Management | Adel Hussien | Orders status integration with backend | Mobile |  | 3 | 5
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Order Customization | Mostafa Mohamed | Customizations separation | Backend |  | 3 | 7
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | Policy & Legal | Mostafa Mohamed | Terms and conditions | Backend |  | 1 | 2
| In Progress | Low | 2025-07-06 | 2025-07-17 | 11 | Support & Information | Loai Tarek | FAQ | Backend |  | 3 | 5
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Customer Service | Mustafa Ibrahim | Customer care design and integration | Mobile |  | 8 | 16
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Guest Access | Mustafa Ibrahim | Guest session integration | Mobile |  | 8 | 14
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Checkout Flow | Mustafa Ibrahim | New interaction design & implementation during checkout | Mobile |  | 5 | 12
| In Progress | Medium | 2025-07-06 | 2025-07-17 | 11 | Branding & UI | Adel Hussien | Splash screen categorization | Mobile |  | 5 | 8
| In Progress | High | 2025-07-06 | 2025-07-17 | 11 | Checkout Flow | Mustafa Ibrahim | New delivery method design | Mobile |  | 5 | 12
| Actions and Recommendations |  | Inquiries |  | Issues |  | Actions | 1
| #1 | sfh | #1 | SMS Provider | #1 | Server Issue caused beta down & delays in testing | Inquiries | 1
| #2 |  | #2 | multi-currancy payment gateway | #2 |  | Issues | 1
| #3 |  | #3 |  | #3
| #4 |  | #4 |  | #4
| #5 |  | #5 |  | #5
| #6 |  | #6 |  | #6
| #7 |  | #7 |  | #7

## Sheet2
Senoirity | Name | Position | Peformance Rating | Quality Rating | Workload Low/Normal/High | Note
Jr | Mustafa Ahmed | Ui/Ux | 4 | 4 | Low
tech-Lead | Aboelhassan Omran | Backend-Dev/ tech lead | 4 | 0 | High
Jr |  | Tester | 4 | 0 | Normal
Jr | Loai Tarek | Backend-Dev | 4 | 0 | Normal
Jr | Mostafa Mohamed | Backend-Dev | 3 | 0 | Normal
Jr | Toka Yasser | Frontend-Dev | 4 | 0 | High
Jr | Ahmed Samy | Frontend-Dev | 5 | 0 | Normal
Jr | Mohamed Hafez | Frontend-Dev | 4 | 0 | High
Mid | Mustafa Ibrahim | Mobile Developer | 4 | 0 | High
Jr | Adel Hussien | Mobile Developer |  |  | Normal